## Sheet1
Requirement ID | Requirement Description | Priority | Estimated time | Actual time
1 | As a Client, I would like to rent a car, so that I can use it | Critical | 17 | 19
2 | As a Client, I would like the option to rent several cars, so that I can use them | High | 13 | 17
3 | As a Client, I would like to indicate a rental period, so that I can return the car/s after it ends. | High | 13 | 0
4 | As a Client, I would like to have the option to choose which type of car I want to rent, so that I can have a better service | Middle | 10 | 10
5 | As an Employee, I would like to know how many clients rented a car so that I can keep track of them. | Low | 10 | 0
6 | As an Employee, I would like to know how many cars are rented so that I can track them | Middle | 12 | 0
7 | As an Employee, I would like to know when a certain client should return a certain car so that I can have an idea about managing that car in the future | Middle | 12 | 0
8 | As an Employee, I would like to set the car’s type so that I can provide a better service for my customers | Middle | 10 | 10
9 | As an Employee, I would like to specify the cars description into a database so that I can have this information saved | High | 13 | 15
10 | As a Client, I would like to choose a place from where I can take and return the car so that I can get an easier way of renting the car | High | 15 | 13
11 | As an Employee, I would like to provide several places of taking and returning the cars so that the customers can get a better service | High | 13 | 12
12 | As an Employee, I would like to add new cars, so that clients have more options | Middle | 13 | 13
13 | As an Employee, I would like to know which cars are currently being for rent, so that I may provide a better service to the rest of the clients | Middle | 13 | 12
14 | As an Employee, I would like to indicate which car is under repair, so that other clients are informed | Low | 8 | 0
15 | As an Employee, I would like to manage a client's rental request, so that I may input accurate information in the system | Middle | 13 | 0
16 | As a Client, I would like to be able to log in, so that my personal and rental information is secured | High | 15 | 18
17 | As a Client, I would like to edit my personal information in case that they were changed or a mistake had occurred | Middle | 11 | 11
18 | As an Employee, I would like to remove cars from the system so that I can exclude cars that are no longer available. | Middle | 11 | 10
19 | As an Employee, I would like to be able to log in, so that I can use the system. | Critical | 11 | 15
|  |  | 233 | 175
[5 empty] | Sprints | Expectation | Actual
|  |  | 68 |  | 0 | 233 | 233
[5 empty] | 1 | 199.7143 | 233
[5 empty] | 2 | 166.4286 | 215
[5 empty] | 3 | 133.1429 | 187
[5 empty] | 4 | 99.8571 | 170
[5 empty] | 5 | 66.5714 | 145
[5 empty] | 6 | 33.2857 | 124
[5 empty] | 7 | 0 | 68